## Sheet1
Carver Center Marketing Priorities
TASK/ ACTIVITY | DATE/ TIMING | PRIORITY STATUS | OBJECTIVE | ACTION PLAN
|  |  |  | Owner | Budget | Timing | Details/Notes
Annual Appeal
Concept/Content Development | 2018-09-06 | High | Meet Fundraising Goal | Joe/Ciara | 0 | Immediate | Ciara and her team at PepsiCo will spend time with Carver's historical pieces and desired language to develop a concept
Approval of Final Piece | 2018-09-20 | High | Meet Fundraising Goal | Joe/Ciara/Julie | 0 | Immediate | Marketing Committee to review final draft
Printing and Electronic Version | 2018-10-01 | High | Meet Fundraising Goal | Joe/Ciara | 6250 | Immediate | Graphic Management can turn around 5,000 pieces in 7 business days
Mail Out | 2018-10-10 | High | Meet Fundraising Goal | Joe/Ciara | 1750 | Immediate | Graphic Management will send from print to post office
Hit Mailboxes | 2018-10-15 | High | Meet Fundraising Goal | Joe/Ciara | 0 | Immediate | Let the money flow
Design Guide
Flyer Design | 2018-08-20 | Completed | Provide Learning Team Staff with a template to populate content with ease and consistency | Jill Singer | 850 | Immediate | Jill will be sending us the final version on 08/20
Slide Decks | October | Medium | Develop Brand Consistency | TBD | TBD | TBD | TBD
Website Consistency | October | Medium | Develop Brand Consistency | TBD | TBD | TBD | TBD
Dec 2 Community Event
Develop a Marketing Plan | 2018-08-29 | High | Honor the client, Create volunteer opportunities, increase visibility | Marketing Committee | 0 | Immediate | Marketing Plan Components (Distribution Strategy, Invite Design, Run of Show, etc.)
Clients Receive Invite | 2018-10-15 | High |  |  |  | Immediate
Sponsorship | 2018-08-24 | High | Funding the Event | Joe | 10000 | Immediate | Ensure working capital- Whole Foods and TD Bank
Carver Scholars
Develop a PR Strategy | 2018-10-15 | High | 1. Create visibility and awareness about our new program format 2. Identify Additional Resources ($75K) | Marketing Committee/ Leanne | 0 | Immediate | Identify local newspapers, media channels, and other outlets that would spolight our story