## Dashboard Status
DASHBOARD 5/7/2025
Strategic Areas of Focus:
|  | Orignal Due Date | On track |  | Status | Notes
|  |  | Yes | No
1-1 | 1-1. Increase the supply of free food through the Carver Market by adding more pick-ups from Feeding Westchester and increasing Retail Recovery activity. | FY 24-Q3 | TRUE | FALSE | Complete and ongoing | We are receiving much more free food from Feeding Westchester than we did in prior years by picking up in between their weekly delivery.
1-2 | 1-2. Hire full-time Carver Market Assistant. | FY 24-Q3 | TRUE | FALSE | Complete | Armando Garcia joined the Carver Market Team in July
2-1 | 2-1. Fully leverage Carver's client database to better serve and communicate with the families who use our current programs. | FY 24-Q3 | FALSE | TRUE | Ongoing Progress | Awaiting full implementation of Zapier/Payment Vehicle
1-3 | 1-3. Expand Carver Market hours of operation. | FY 24-Q4 | TRUE | FALSE | Plans in Progress | Aiming for fall opening on Saturdays.
1-4 | 1-4. Source and secure new walk-in freezer and refrigerator, and ensure backup power to increase storage capacity and manage the increased need to store food for both food services and Carver Market departments. | FY 24-Q4 | FALSE | TRUE | Walk-Ins Installed | Walk-ins are installed. Generator Project was not funded.
1-9 | 1-9. Rebrand Teen Center with a new name and strengthen programs. | FY 24-Q4 | TRUE | FALSE | Complete | Abandoned name change. Programming is robust and Teen Center participation has increased from 100 to 300 participants
1-5 | 1-5. Hire a full-time Aquatics Assistant Director for program expansion. | FY 25-Q1 | TRUE | FALSE | Complete | Hired a part-time Assistant Aquatics Director who focusses on Swim Academy Administration.
1-6 | 1-6. Implement staff development program to grow aquatics staff. | FY 25-Q1 | TRUE | FALSE | Plans in Progress | As of February, six staff members have obtained their Lifeguard Instructor Certification to help with this process. In addition, we are currentlyhosting two staff training workshops per month.
2-2 | 2-2. Expand staffing support to include a full-time bilingual marketing/external affairs position. | FY 25-Q1 | TRUE | FALSE | Complete | Re-organized the advancement staff to give opportunity to our Advancement Director (Olivia) to take on this role as a part-time responsibility within her job description.
3-1 | 3-1. Develop a diversity, equity, and inclusion plan, policy, and statement. | FY 25-Q1 | FALSE | TRUE | Delayed | Bumped this project out.
4-1 | 4-1. Hire full-time Development Associate to execute strategies 4-3 to 4-6. | FY 25-Q1 | TRUE | FALSE | Complete | Amended the plan to hire a part-time grantwriter and a full-time Advancement Coordinator.
4-2 | 4-2. Establish a board level ad hoc committee to explore how to maximize/grow the Carver Center endowment. | FY 25-Q1 | TRUE | FALSE | Amended | Finance Committee moved funds to maximize growth.
2-3 | 2-3. Increase social media presence. | FY 25-Q2 | TRUE | FALSE | Ongoing Progress | Advancement Director has expanded our social media presence. New Linked-In initiatives are underway.
2-4 | 2-4. Refresh marketing materials. | FY 25-Q2 | TRUE | FALSE | In development. Now a post-Gala priority. | Currently creating new rack cards and a brochure. In design and editing phase.
3-2 | 3-2. Using tools such as Nonprofit Westchester's Compensation Report, create a plan for salary recalibration for next three years. | FY 25-Q2 | FALSE | TRUE | Ongoing Progress | Used this tool (Nonprofit NY) for FY25 budget. Completed Westchester 2025 survey. Planning adjustments where needed for FY26.
3-3 | 3-3. Refine organizational chart and rewrite job descriptions to provide greater depth in responsibility and accountability. | FY 25-Q2 | FALSE | TRUE | In early development | Carver has created a number of new positions in FY25. May & June evaluation process includes updating of job descriptions.
1-12 | 1-12. Secure funding for case management professional staff to ensure continuation and growth of this new program. | FY 25-Q3 | TRUE | FALSE | In early development | Currently spending down the last of our start-up grant; received new funding from Field Hall in FY25; have support from one other foundation. Additional applications to the Department of Health and Office of Cannabis Management have been submitted.
3-4 | 3-4. Develop succession plans and build talent pipeline for board and staff, and plan pathways for staff career advancement. | FY 25-Q3 | TRUE | FALSE | In early development | Nominating Committee working on succession for treasurer and president and committee chairs. Have multiple employees in leadership programs. Several promotions have taken place recently (Nutrition/Wellness; Advancement; Teen Center)
1-7 | 1-7. Expand focus on water safety by increasing the program times for the Learn to Swim, Lap Swim, and Family Swim from three days to five. | FY 25-Q4 | TRUE | FALSE | Halfway to goal | Increased Carver's water safety programs from three days to four in fall '24. Received a grant from Stew Leonards Learn to Swim program to provide water safety instruction starting in Spring 2025.
2-5 | 2-5. Develop and implement an annual communications plan to include internal and extremal audiences. | FY 25-Q4 | TRUE | FALSE | In early development
3-5 | 3-5. Create a plan for streamlining and improving cultivation, recruitment, overall volunteer experience at Carver Center. | FY 25-Q4 | TRUE | FALSE | In early development | Volunteer Management has been moved from G&A to Advancement. Volunteer tracking and communication through Apricot in development.
3-6 | 3-6. Update the benefits program to better serve employees and increase participation in retirement and health plans. | FY 25-Q4 | TRUE | FALSE | Ongoing Progress | New 401K program launched in January 2025. Health insurance proposal will be submitted to board in advance of June board meeting.
3-7 | 3-7. Strengthen systems and annual budget for employee professional development opportunities. | FY 25-Q4 | TRUE | FALSE | Ongoing | Leadership Workshop participation is robust: Karina, Colleen, Daisy, Olivia. Key staff participates regularly in NPW workshops.
4-3 | 4-3. Pursue government grants that aligned with Carver Center programs for youth services and workforce development programming for emerging young adults. | FY 25-Q4 | TRUE | FALSE | Ongoing Progress with great success | LEAPS funding will provide $900,000 for each of five years; Workforce development launched in FY24 with substantial funding. Applying for a "Boost" grant for FY26.
4-4 | 4-4. Increase unrestricted contributions by 5%. | FY 25-Q4 | TRUE | FALSE | In early development | Advancement Coordinator hired. Goal exceeded. Developing strategies to expand overall number of donors .
2-6 | 2-6. Update and refresh the website. | FY 26-Q2 | TRUE | FALSE | Not yet started | Budgeting for costs in FY26.
3-8 | 3-8. Cross-train staff on key systems (i.e., Apricot 360and Raiser's Edge NXT). | FY 26-Q2 | TRUE | FALSE | Underway.
1-8 | 1-8. Expand swim program to include private swim lessons, more water safety instruction, water aerobics, and other classes, and establish a swim team. | FY 26-Q4 | TRUE | FALSE | Well ahead of schedule | Swim Team began in FY24 with a Youth Sports Grant and is continuing in FY25. New Aquatics Director hired April 2025.
4-5 | 4-5. Create, fund, and implement a 3 year capital improvement plan to ensure that Carver Center facilities can house program needs and to address deferred maintenance needs. | FY 27-Q2 | TRUE | FALSE | In early development | Capital Facilities Plan for FY25 with significant funding is underway. Mike Walsh identified to lead Board Facilities Committee! Begun to hire professional expertise (architect/engineer) in addition to pro-bono advisor.
1-10 | 1-10. Sustain Carver's commitment to developing and offering affordable afterschool programs for elementary and middle school children with support from community stakeholders and partners as opportunities afford. | ongoing | TRUE | FALSE | Ongoing | Elementary afterschool is funded at two schools for 5 years; funded at the other two schools through next year. Middle School began RECOVS for 1.5 years. Additional LEAPS funding may become available.
1-11 | 1-11. Strengthen Scholarship Program to support youth with scholarships through all years of post-secondary education and to program coaching for scholarship recipients to help them navigate their journey and improve outcomes. | ongoing | TRUE | FALSE | Well underway | Funding expanded to $58,000 in FY25. Program Committee is analyzing our goals; staff is preparing impact measurement report.
4-6 | 4-6. Grow the fundraising program by increasing the number of major donors by 5% year over year. | ongoing | TRUE | FALSE | Ongoing | Expansion of Advancement Department implemented. Committee goals for FY25 align with the strategic planning goal. Analysis from FY25 underway.
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Colleen Kane updated
Note on G33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Colleen Kane updated

## Dashboard
DASHBOARD
Strategic Areas of Focus:
| Program Expansion | Blue
| Marketing & Communications | Orange
| Talent | Pink
| Financial Sustainability | Green
|  | FY 24 |  |  |  | FY 25 |  |  |  | FY 26 |  |  |  | FY 27
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | Jul-Sept | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sept | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sept | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sept | Oct-Dec | Jan-Mar | Apr-Jun
1-1 | 1-1. Increase the supply of free food through the Carver Market by adding more pick-ups from Feeding Westchester and increasing Retail Recovery activity. | bar: FY 24 Q3
1-2 | 1-2. Hire full-time Carver Market Assistant. | bar: FY 24 Q3
2-1 | 2-1. Fully leverage Carver's client database to better serve and communicate with the families who use our current programs. | bar: FY 24 Q3
1-3 | 1-3. Expand Carver Market hours of operation. | bar: FY 24 Q4
1-4 | 1-4. Source and secure new walk-in freezer and refrigerator, and ensure backup power to increase storage capacity and manage the increased need to store food for both food services and Carver Market departments. | bar: FY 24 Q4
1-9 | 1-9. Rebrand Teen Center with a new name and strengthen programs. | bar: FY 24 Q4
1-5 | 1-5. Hire a full-time Aquatics Assistant Director for program expansion. | bar: FY 25 Q1
1-6 | 1-6. Implement staff development program to grow aquatics staff. | bar: FY 25 Q1
2-2 | 2-2. Expand staffing support to include a full-time bilingual marketing/external affairs position. | bar: FY 25 Q1
3-1 | 3-1. Develop a diversity, equity, and inclusion plan, policy, and statement. | bar: FY 25 Q1
4-1 | 4-1. Hire full-time Development Associate to execute strategies 4-3 to 4-6. | bar: FY 25 Q1
4-2 | 4-2. Establish a board level ad hoc committee to explore how to maximize/grow the Carver Center endowment. | bar: FY 25 Q1
2-3 | 2-3. Increase social media presence. | bar: FY 25 Q2
2-4 | 2-4. Refresh marketing materials. | bar: FY 25 Q2
3-2 | 3-2. Using tools such as Nonprofit Westchester's Compensation Report, create a plan for salary recalibration for next three years. | bar: FY 25 Q2
3-3 | 3-3. Refine organizational chart and rewrite job descriptions to provide greater depth in responsibility and accountability. | bar: FY 25 Q2
1-12 | 1-12. Secure funding for case management professional staff to ensure continuation and growth of this new program. | bar: FY 25 Q3
3-4 | 3-4. Develop succession plans and build talent pipeline for board and staff, and plan pathways for staff career advancement. | bar: FY 25 Q3
1-7 | 1-7. Expand focus on water safety by increasing the program times for the Learn to Swim, Lap Swim, and Family Swim from three days to five. | bar: FY 25 Q4
2-5 | 2-5. Develop and implement an annual communications plan to include internal and extremal audiences. | bar: FY 25 Q4
3-5 | 3-5. Create a plan for streamlining and improving cultivation, recruitment, overall volunteer experience at Carver Center. | bar: FY 25 Q4
3-6 | 3-6. Update the benefits program to better serve employees and increase participation in retirement and health plans. | bar: FY 25 Q4
3-7 | 3-7. Strengthen systems and annual budget for employee professional development opportunities. | bar: FY 25 Q4
4-3 | 4-3. Pursue government grants that aligned with Carver Center programs for youth services and workforce development programming for emerging young adults. | bar: FY 25 Q4
4-4 | 4-4. Increase unrestricted contributions by 5%. | bar: FY 25 Q4
2-6 | 2-6. Update and refresh the website. | bar: FY 26 Q2
3-8 | 3-8. Cross-train staff on key systems (i.e., Apricot 360and Raiser's Edge NXT). | bar: FY 26 Q2
1-8 | 1-8. Expand swim program to include private swim lessons, more water safety instruction, water aerobics, and other classes, and establish a swim team. | bar: FY 26 Q4
4-5 | 4-5. Create, fund, and implement a 3 year capital improvement plan to ensure that Carver Center facilities can house program needs and to address deferred maintenance needs. | bar: FY 27 Q2
1-10 | 1-10. Sustain Carver's commitment to developing and offering affordable afterschool programs for elementary and middle school children with support from community stakeholders and partners as opportunities afford. | FY 24 Q1: Ongoing
1-11 | 1-11. Strengthen Scholarship Program to support youth with scholarships through all years of post-secondary education and to program coaching for scholarship recipients to help them navigate their journey and improve outcomes. | FY 24 Q1: Ongoing
4-6 | 4-6. Grow the fundraising program by increasing the number of major donors by 5% year over year. | FY 24 Q1: Ongoing